INTRODUCTORY ROBOTICS · UNIT 2: PROJECT MANAGEMENT Project Planning: Decision Matrix, WBS & Gantt Chart Class 7 of 8 · Unit 2, Class 2 of 3 · 74 minutes

| NAME _______________________________ | TEAM _______________________________ | DATE _______________________________ | PERIOD _____________________________ |
| --- | --- | --- | --- |

LEARNING OBJECTIVES 1. Apply a weighted decision matrix to select the best collector module concept from Class 6. 2. Break the selected concept into a Work Breakdown Structure (WBS) with phases, tasks, owners, and time estimates. 3. Plot tasks on a Gantt chart with milestones and identify the critical path. 4. Complete a build-ready design specification your Builder can execute without asking any questions.

PART 1  ·  PLANNING TOOLS — READING & DISCUSSION  (12 MIN)

Plans Beat Intentions

A Work Breakdown Structure (WBS) breaks a project into phases, tasks, and subtasks until every piece of work is small enough that one person can own, estimate, and complete it. Then a Gantt chart puts each task on a timeline so the team can see what is happening now and what is at risk. Some tasks have dependencies — Task B cannot start until Task A is done. The chain of dependent tasks that determines total project duration is the critical path. If any task on the critical path slips, the whole project is late. Tasks not on the critical path have float — they can slip a little without delaying the end date. A milestone is a verifiable checkpoint, not a task. Either the condition is met or it isn’t. Always add buffer — 10–20% extra time on every estimate — to absorb unexpected problems.

I DO — Teacher models WBS decomposition and critical path thinking

Decomposing the collector module project into phases: Phase 1 — Design & Selection (today, Class 7) Phase 2 — Gather & Prep (Class 8, first 10 min) Phase 3 — Build (Class 8, 10–45 min) Phase 4 — Test & Iterate (Class 8, 45–74 min) Finding the critical path: Every build task is sequential — you can’t attach the mechanism before the bracket is done. The entire build phase is on the critical path. However, the Documenter can write up the design spec while the Builder is fabricating — that is parallel, not on the critical path. Buffer: Add 10% to every build task. A dropped screw, a wrong-size bracket, or a misunderstood instruction each costs 3–5 minutes. Buffer absorbs these without derailing the milestone.

1.  What is the critical path in your collector module build, and why does it matter more than the total number of tasks?

2.  Name one task in your module build that could run in parallel with the critical path. Explain why it doesn’t block the build.

| 🟢 NOVICE Answer Q1 using: “The critical path matters because if [task] slips, then [next task] also slips...” | 🔵 INTERMEDIATE Answer both questions. Sketch a simple arrow diagram: 3 sequential tasks (critical path) and 1 parallel task branching off. | 🟣 PROFICIENT Answer both questions. Calculate: if the critical path has 5 tasks averaging 12 min each with 10% buffer, what is total critical path time? Does it fit in one class period? |
| --- | --- | --- |

PART 2  ·  WEIGHTED DECISION MATRIX  (18 MIN)

Let the Data Choose

A weighted decision matrix removes personal preference from concept selection. Set criteria, assign weights before scoring, then score each concept. The highest total weighted score wins. The Lead Engineer owns this process and makes the final call — but must document any override reasoning before the build starts.

I DO — Teacher models scoring one criterion live

Criterion: Build time (weight 5 — highest priority, only one class period to build) Concept A — passive funnel: score 5/5. Needs 4 channels + 2 brackets + 8 bolts. Estimated build time: 20 min. Weighted score: 5 × 5 = 25. Concept B — servo claw: score 2/5. Needs servo mounting, programming, claw stroke test. Estimated build time: 45+ min. Weighted score: 5 × 2 = 10. What a valid override looks like: “We are overriding the matrix. Concept A scored higher on build time, but we choose Concept B because its ability to collect balls from corners outweighs the build time risk — we have practiced servo assembly and estimate 25 minutes.” That reasoning is documented. If it turns out to be wrong, the notebook shows the thinking.

YOU DO — Complete Your Team’s Decision Matrix

Score your three concepts from Class 6. Set all weights before entering any scores. Add up to two additional criteria in the blank rows.

| Criterion | Weight (1–5) | Concept A Score | Concept A Wtd | Concept B Score | Concept B Wtd | Concept C Score | Concept C Wtd |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Collects cubes effectively | 5 |  |  |  |  |  |  |
| Collects balls effectively | 4 |  |  |  |  |  |  |
| Build time (one class period) | 5 |  |  |  |  |  |  |
| Fits within 6-inch limit | 5 |  |  |  |  |  |  |
| Driver controllability | 4 |  |  |  |  |  |  |
| Failure risk (lower = higher score) | 3 |  |  |  |  |  |  |
| REV parts availability | 3 |  |  |  |  |  |  |
| Add criterion: |  |  |  |  |  |  |  |
| Add criterion: |  |  |  |  |  |  |  |
| TOTAL WEIGHTED SCORE |  |  |  |  |  |  |  |

3.  Which concept won the matrix? Was it your team’s instinctive favorite from Class 6? If the winner differs, write one sentence explaining how your team will decide — using your charter’s decision-making protocol.

NOTEBOOK (Documenter): Record the complete decision matrix now. Circle the winner. If the Lead Engineer overrides the matrix, write the override reason verbatim before any build work begins.

| 🟢 NOVICE Fill in scores for all 7 pre-set criteria. Calculate weighted scores (weight × score). Sum each concept column for the total. | 🔵 INTERMEDIATE Complete all rows including your two added criteria. Answer Q3 with explicit reference to your Class 6 charter’s decision-making protocol. | 🟣 PROFICIENT Complete the matrix and Q3. Run a sensitivity check: if you changed one weight by ±1, would the winner change? What does that tell you about confidence in the result? |
| --- | --- | --- |

PART 3  ·  WORK BREAKDOWN STRUCTURE & GANTT CHART  (22 MIN)

Break It Down, Then Map It Out

Complete the WBS first — fill in owner and done-when columns, and add at least two concept-specific tasks in the blank rows. Then fill in the Owner column on the Gantt chart.

| Task / Subtask | Owner (role) | Est. time | Done when… (your milestone) |
| --- | --- | --- | --- |
| ▶ Phase 1 — Design & Selection (Today, Class 7) |  |  |  |
| Run decision matrix on all 3 concepts | Lead Engineer | 15 min | Matrix complete, concept circled |
| Draw final annotated design sketch | Lead Engineer | 10 min | Sketch in notebook, two views, labeled |
| Create parts list | Builder | 5 min | Every part named with qty and source |
| Build design specification | Lead Engineer | 8 min | Spec complete — Builder can start without questions |
| ▶ Phase 2 — Gather & Prep (Class 8, first 10 min) |  |  |  |
| Retrieve parts from storage | Builder | 5 min | All parts at workstation |
| Verify parts against list | Builder + Lead Eng. | 5 min | Every item confirmed or substitution noted |
| ▶ Phase 3 — Build (Class 8, 10–45 min) ◆ Milestone: module attached to MiniBot |  |  |  |
| Fabricate mount bracket / frame |  |  |  |
| Attach collector mechanism to frame |  |  |  |
| Attach module to MiniBot + function check |  |  | Module stays attached through 3 ft drive + 90° turn |
| Concept-specific task: |  |  |  |
| Concept-specific task: |  |  |  |
| ▶ Phase 4 — Test & Iterate (Class 8, 45–74 min) ◆ Trial 1 ◆ Trial 2 |  |  |  |
| Trial 1 — teleop run, log data | Documenter | 10 min | Time + object count recorded in notebook |
| Debrief: identify top 1–2 changes | Lead Eng. + Team | 5 min | Change decision written in notebook |
| Implement change + Trial 2 | Builder | 15 min | Trial 2 data recorded + compared to Trial 1 |

Gantt Chart — fill in the Owner column and shade planned bars

Shade the bar cells with a pencil to show when each task is planned. Mark milestones with a diamond (◆). The Project Manager should have a clean copy of this Gantt at the start of Class 8.

| Task | Owner | C7 Open | C7 Mid | C7 End | C8 Open | C8 Mid | C8 End |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 — Design & Selection ◆ Spec complete |  | ███ |  |  |  |  |  |
| Phase 2 — Gather & Prep |  |  |  |  | ███ |  |  |
| Phase 3 — Build ◆ Module on MiniBot |  |  |  |  |  | ███ |  |
| Phase 4 — Test & Iterate ◆ Trial 1 ◆ Trial 2 |  |  |  |  |  |  | ███ |

4.  Which single task is most likely to make the whole project late if it slips? What is your team’s contingency if that happens?

PART 4  ·  FINAL DESIGN SPECIFICATION & SKETCH  (15 MIN)

From Decision to Build-Ready

A design specification is a written contract for the build: what the module must do, every constraint it must satisfy, and the complete parts list. A good spec means the Builder can start without asking any questions. Every question asked during the build is a spec gap.

📄 Collector Module Design Specification

| Spec field | Your team’s response |
| --- | --- |
| Selected Concept Name |  |
| Performance Requirement What must it do? | The module must collect at least ___ cubes / balls per ___ seconds of teleop. The driver must be able to... |
| Physical Constraints All must be satisfied | Must not extend more than 6 inches from the robot frame. Must attach and detach with bolts — no permanent modifications. Robot must drive normally with module attached... |
| Parts List Every part, size, quantity | REV 15mm channel × _ REV side mount bracket × _ M3 × 8mm hex bolt × _ M3 nyloc nut × _ ... |
| Known Risks What could go wrong? | Risk 1: ... Risk 2: ... Risk 3: ... |

Final annotated design sketch — draw your selected concept below. Include a top view AND a front view. Label all key parts and note at least two dimensions. This is the build reference your Builder will use in Class 8.

Final annotated design sketch — top view + front view + key dimensions

5.  Which part of the design specification did your team debate longest? How did your charter’s decision-making protocol resolve it?

PART 5  ·  NOTEBOOK ENTRY & EXIT REFLECTION  (7 MIN)

Document and Reflect

NOTEBOOK (all roles) — confirm before signing: - Complete decision matrix with winner circled (and override reasoning if applicable) - Final annotated sketch — two views, dimensions, all parts labeled - Design specification with complete parts list - WBS with owner, time estimate, and done-when for every task Project Manager: bring a clean copy of the Gantt chart to Class 8 for the build-start check-in.

1.  What is the difference between a task and a milestone on a Gantt chart? Give one example of each from your module build plan.

2.  Your matrix says Concept A wins, but the Lead Engineer prefers Concept C. Write the exact sentence from your Class 6 charter that determines how this gets resolved.

3.  Review your Gantt. Which milestone is most at risk? Name one specific action you will take at the very start of Class 8 to protect it.

4.  Self-assessment — circle one per row:

| Objective | Not yet | Getting there | Got it |
| --- | --- | --- | --- |
| I can define WBS, Gantt, critical path, milestone, and float in my own words | ○ | ○ | ○ |
| Our decision matrix has scores and weighted totals for all 7+ criteria, with a winner identified | ○ | ○ | ○ |
| Our WBS has every task with an owner, time estimate, and done-when milestone | ○ | ○ | ○ |
| Our design spec is complete enough that the Builder can start without asking any questions | ○ | ○ | ○ |

Extension / Exploration Calculate the critical path through your WBS: list every Phase 3 (Build) task in sequence and total the time estimates with 10% buffer. Is it possible to complete the build phase and two test trials in one 74-minute class period? If not, which task would you cut or compress, and what would you lose? Write your analysis in the notebook and label it “Critical Path Analysis — Class 7.”