INTRODUCTORY ROBOTICS · UNIT 2: PROJECT MANAGEMENT FOR ENGINEERING TEAMS Unit 2 Assessment Roles & Charters · Decision Matrix · WBS & Gantt Chart · Risk Management & Iteration

| NAME _______________________________ | TEAM _______________________________ | DATE _______________________________ | PERIOD _____________________________ |
| --- | --- | --- | --- |

| Section 1: Bank (20) | Section 2: FR (30) | Section 3: Task (50) | Total (100) | Grade |
| --- | --- | --- | --- | --- |

INSTRUCTIONS Section 1 — Answer Bank (20 pts): Write the letter of the best answer on the line next to each question. Each answer may be used only once. Two answers will not be used. Section 2 — Free Response (30 pts): Answer in complete sentences. Points are shown next to each question. Section 3 — Performance Task (50 pts): Complete the task fully. Partial credit is awarded. You may use your engineering notebook as a reference. Show all calculations in Section 3.

Section 1 — Answer Bank 10 questions · 2 points each · 20 points total

Directions: Choose the best answer for each question from the Answer Bank below. Write the letter of your answer on the line provided. Each answer may be used only once. Two answers in the bank will not be used.

ANSWER BANK A. The Lead Engineer, with documented reasoning written before the build begins B. Likelihood × Impact C. A team charter D. Critical path E. Milestone F. Float G. Mitigation strategy H. Project Manager I. Hypothesis J. The change does not target the specific failure pattern shown in the data K. Buffer L. Design specification

1.  ____  A team is deciding who has final say over scheduling conflicts versus technical design conflicts. What document should they have written before this question ever came up?

2.  ____  A team’s decision matrix gives Concept A the highest weighted score, but the team builds Concept B instead. According to the rules of a valid override, who is allowed to make this call, and what must happen first?

3.  ____  A WBS shows five sequential, dependent tasks and one task that can run in parallel without blocking the others. If any of the five sequential tasks slips, the whole project is late. What is this chain of five tasks called?

4.  ____  “Module attached to the robot and the robot drives normally” is written on a Gantt chart as a verifiable checkpoint, not a task with a duration. What is this called?

5.  ____  A task is not on the critical path and can slip by two days without delaying the project’s end date. What is this slack time called?

6.  ____  A team adds 10% extra time to every build task estimate, planned in advance, to absorb small unexpected problems like a dropped screw or a wrong-size bracket. What is this practice called?

7.  ____  In a risk register, a risk is scored on a 1–3 scale for how likely it is to happen and a separate 1–3 scale for how serious it would be. How is the overall priority score calculated?

8.  ____  A team writes in their risk register: “Risk: module might detach during a trial. Action: add a second mounting bolt and hand-test before Trial 1.” What is this written action called?

9.  ____  Trial 1 data shows a robot’s collector missed every ball attempt but successfully grabbed every cube attempt. A team proposes simply making the entire intake bigger without addressing why balls specifically failed. What is the core problem with this proposed iteration?

10.  ____  A team writes: “We believe the claw’s closing angle is too narrow for the ball’s diameter, causing the grip to fail before fully surrounding it.” This is a testable prediction connecting test data to a proposed change. What is this called?

Section 2 — Free Response 3 questions · 30 points total

11.  Team Decision-Making & the Charter  (10 pts)

(a)  Explain, in your own words, why a team should write its decision-making protocol before any disagreement happens — rather than figuring it out in the moment when a conflict arises. (3 pts)

(b)  Your team’s decision matrix gives Concept A a score of 94 and Concept B a score of 81. The Lead Engineer says she prefers Concept B because it handles balls more reliably. Describe exactly what must happen for this preference to be a valid override — and what would make it invalid. (4 pts)

(c)  Describe a real or hypothetical moment where your team’s decision-making protocol was tested. What happened, and how did the protocol guide the outcome? (3 pts)

12.  Hypothesis-Driven Iteration  (10 pts)

(a)  Explain the difference between a random fix and a hypothesis-driven iteration. Use a specific example from your collector module build. (4 pts)

(b)  A team’s Trial 2 score is identical to their Trial 1 score after making a hypothesis-driven change. One team member says, “That was a waste of time.” Explain why this team member is incorrect. (3 pts)

(c)  Describe one iteration your team made during Class 8 — your hypothesis, your change, and whether the result confirmed or denied your hypothesis. (3 pts)

13.  Risk Management as Purposeful Design  (10 pts)

(a)  Explain why “hope it doesn’t happen” fails as a mitigation strategy. Connect your answer to purposeful design from Unit 1. (4 pts)

(b)  A risk has a likelihood of 3 and an impact of 2. Calculate its priority score and explain whether the team should treat this risk as “Monitor,” “Significant,” or “Critical,” using the risk matrix from class. (3 pts)

(c)  Describe one risk that actually occurred during your team’s build or testing, and explain how your mitigation strategy held up — or what you would change next time. (3 pts)

Section 3 — Performance Task 1 task · 50 points total

Task 1.  Risk Register & Partial Gantt Chart for a Novel Scenario  (50 pts)

Scenario: A different robotics team is designing a brand-new attachment: a “flag deployer” module that must raise a small flag to a height of 12 inches within the last 10 seconds of a match. The module attaches to their robot using REV hardware, must not exceed a 4-inch footprint, and must be triggered by a single button press from the driver. The team has one 74-minute class period to design, build, and test this module before their first competition match. Your task: Using everything you learned in Unit 2, build a risk register for this new project and create a partial Gantt chart showing how the team should plan their single class period.

GRADING CRITERIA — TASK 1 - Risk register: at least 6 distinct risks across 3+ categories (design, parts, build, driver, time) — 12 pts - Risk register: likelihood, impact, and priority score (L×I) correctly calculated for every risk — 10 pts - Risk register: every risk with priority 6+ has a specific, actionable mitigation strategy — 10 pts - Gantt chart: 4+ phases/tasks placed on a timeline within 74 minutes, with 1+ milestone marked — 10 pts - Written justification: explains highest-priority risk and how it shaped the Gantt timing — 8 pts

Part A — Risk Register

Identify at least 6 risks for the flag deployer project. Score each on likelihood (1–3) and impact (1–3), calculate the priority score, and write a specific mitigation strategy for any risk scoring 6 or higher.

| Risk description | Likeli- hood | Impact | Priority (L×I) | Mitigation strategy (required if priority ≥ 6) |
| --- | --- | --- | --- | --- |

Part B — Partial Gantt Chart (single 74-minute class period)

Plan the team’s single class period. List at least 4 phases or tasks in the order they should happen, with a rough time estimate for each. Mark at least one milestone with a ◆ symbol.

| Order | Phase / task | Time estimate | Milestone? (mark ◆ if yes) |
| --- | --- | --- | --- |

Part C — Written Justification

Identify which single risk from your register has the highest priority score. Explain why, and describe specifically how this risk influenced the order or timing of tasks in your Gantt chart above.

Answer Key & Scoring Notes (Teacher Copy)

Section 1 Answer Bank: 1-C, 2-A, 3-D, 4-E, 5-F, 6-K, 7-B, 8-G, 9-J, 10-I. Unused answers: H (Project Manager) and L (Design specification). Section 2: See rubric. FR11b: full credit requires both halves — documented reasoning AND that the documentation happens before the build begins. FR12b: full credit requires identifying that a denied hypothesis is still useful data, not wasted effort. FR13a: full credit requires connecting the lack of action to the absence of purposeful reasoning, mirroring Unit 1’s “why did you build it that way?” standard. Section 3: Any 6 distinct, plausible risks for a flag-deployer project are acceptable (design risk: mechanism doesn’t reach 12"; parts risk: missing 4" footprint fasteners; build risk: button trigger circuit not seated; driver risk: button pressed too early/late; time risk: 74 minutes is tight). Do not award mitigation credit for vague entries like "be careful." Gantt should roughly show: design/plan → build → attach → test, with the test-and-confirm milestone clearly marked given the 10-second end-of-match trigger window is itself a risk worth flagging.